## CPTU Plan
[8 empty] | Ministry/Division: Ministry of Commerce (MoC) | [6 empty] | Budget: Revenue
Agency: Office of the Registrar of Joint Stock Companies (RJSC)
Procurement Entity Name & Code: Office of the Registrar of Joint Stock Companies and Firms & 1735
Annual Procurement Plan
Package No. | Description of procurement package GOODS | Unit | Quantity | Procurement Method & Type | Contract Approving Authority | Source of Fund | Estd. Cost in Tk. | Time Code for Process | Not Used in GOODS | Invite/Advertise Tender | Tender Opening | Tender Evaluation | Approval to Award | Notification of Award | Signing of Contract | Total time to Contract Signature | Time for Completion of Contract
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
LOT - 1 | Computer Server (Server=13, SAN Storage=2, SAN Switch=4, Backup Storage with Software=1, Rack=1, Domain Threat Protection with SSL=2, Vmware Vsphere with SRM VXLAN=1, Vmware Vcenter=1 & Web Application Security=2 for DC-DR) | Lot | 1 (DC & DRS) | OTM (NCT) | MoC | GOB | 53360000 | Planned Dates |  | 1st Sep, 2019 | 22nd Sep, 2019 | 29th Sep, 2019 | 1st Oct, 2019 | 2nd Oct, 2019 | 6th Oct, 2019 |  | 5th Oct, 2022
[8 empty] | Planned Days |  |  | 21 days | 7 days | 2days | 1day | 4 days | 35 days | 1095 days
Actual Dates
LOT-2 | Communication Devices (Router=3, UTM/Firewall=2, Switches=6 etc.) & Dark Fiber Connectivity (DC-DR) | Lot | 1 (DC-DRS) | OTM (NCT) | MoC | GOB | 10020000 | Planned Dates |  | 1st Sep, 2019 | 22nd Sep, 2019 | 29th Sep, 2019 | 1st Oct, 2019 | 2nd Oct, 2019 | 6th Oct, 2019 |  | 5th Oct, 2022
[8 empty] | Planned Days |  |  | 21 days | 7 days | 2days | 1day | 4 days | 35 days | 1095 days
Actual Dates
LOT-3 | Oracle 12c (Database & Weblogic) License Renew for DC-DR | Lot | 1 (DC-DR) | OTM (NCT) | MoC | GOB | 36599247 | Planned Dates |  | 1st Sep, 2019 | 22nd Sep, 2019 | 29th Sep, 2019 | 1st Oct, 2019 | 2nd Oct, 2019 | 6th Oct, 2019 |  | 5th Oct, 2020
[8 empty] | Planned Days |  |  | 21 days | 7 days | 2days | 1day | 4 days | 35 days | 365 days
Actual Dates
LOT-4 | Miscelleneous (Antivirus, CC Camera, Desktop PC, Laptop, Printer & Photocopier Toner, Office Decoration, Furniture, Stationary etc.) | Lot | 1 | OTM (NCT) | MoC | GOB | 2500000 | Planned Dates |  | 1st Sep, 2019 | 22nd Sep, 2019 | 29th Sep, 2019 | 1st Oct, 2019 | 2nd Oct, 2019 | 6th Oct, 2019 |  | 5th Oct, 2020
[8 empty] | Planned Days |  |  | 21 days | 7 days | 2days | 1day | 4 days | 35 days | 365 days
Actual Dates
| Total Value of Goods Procurement | [5 empty] | 102479247
In Word: Ten crore Twenty four lakh seventy nine thousand two hundred forty seven taka only